## Sheet1
ID | Story | Estimation (hours) | Priority (1-5) | Sprint When Finished
1 | Set up a PostgreSQL database on AWS using Docker | 3 | 3 | 1
2 | Design and implement the database schema for inventory | 4 | 4 | 1
4 | Set up a Node.js/Express.js project structure | 3 | 1 | 1
5 | Implement user authentication in the API | 5 | 5 | 1
7 | Set up a React project structure for the front-end | 3 | 1 | 1
8 | Implement login and registration pages in React | 5 | 4 | 1
9 | Connect the React front-end to the Node.js API for authentication | 4 | 2 | 1
16 | Figure out best way to convert invoice info | 2 | 1 | 1
22 | Update Database Schema | 2 | 5 | 1
23 | Create API endpoints for login | 8 | 5 | 1
24 | Collapsible sidebar on all pages | 4 | 3 | 1
25 | Logout setup | 3 | 4 | 1
3 | Populate the database with sample inventory data | 2 | 1 | 2
6 | Create API endpoints for inventory management | 8 | 1 | 2
10 | Design the inventory management UI in React | 6 | 2 | 2
11 | Implement inventory listing in the React app | 4 | 2 | 2
12 | Implement adding new inventory items in the React app | 5 | 2 | 2
19 | Design the dashboard for the app | 5 | 2 | 2
27 | Fix project crashing on refresh | 3 | 3 | 2
28 | Password security - 8 chars, special char, numbers, capital | 2 | 5 | 2
30 | Create Jobs page frontend | 4 | 5 | 2
31 | Fix Logout to guarantee modal operation | 1 | 2 | 2
32 | Add out of stock/instock in inventory page | 2 | 3 | 2
33 | Fix top bar stutter | 3 | 5 | 2
34 | Add change quantity implementation | 3 | 3 | 2
36 | Implement checkbox filtering | 2 | 5 | 2
40 | Remove duplicates in filter | 1 | 2 | 2
41 | Added charts to the dash | 3 | 1 | 2
43 | Add Jobs table to database | 1 | 4 | 2
44 | Create a route for the jobs page | 1 | 4 | 2
48 | Create a filter for the Jobs page | 2 | 3 | 2
49 | Connecte the add jobs button with the API | 3 | 4 | 2
51 | Create the title for the Frontend of the jobs page | 0.5 | 4 | 2
52 | Implement a dropdown function for each job | 1 | 4 | 2
53 | Setup a Reverse Proxy | 4 | 2 | 2
54 | Created Self-Signed SSL certificates | 0.5 | 2 | 2
55 | Add put, get, post, patch to products api | 4 | 4 | 2
56 | Updated the REST API to use HTTPS instead of HTTP | 2 | 2 | 2
57 | Updated the React App to use HTTPS instead of HTTP | 1 | 2 | 2
59 | Fix the JWT in the Front End to kick a user once the JWT has expired | 1.5 | 3 | 2
60 | Allow users to edit information such as username, password, and email | 5 | 4 | 2
62 | Add Purchases table to database | 6 | 4 | 2
63 | Create a route for the purchases page | 1 | 3 | 2
66 | Create a filter for the purchases page | 1.5 | 3 | 2
13 | Implement inventory warnings and notifications | 4 | 1
14 | Deploy the Node.js API on AWS using Docker | 4 | 1
15 | Deploy the React front-end on AWS using Docker | 4 | 1
17 | Compute average based on past invoices | 3 | 1 | 3
18 | Design the inventory management page | 5 | 3 | 3
20 | Design the invoice management page | 5 | 3 | 3
21 | Scanner for the invoices to automatically insert data | 5 | 2 | 3
26 | Set up a setting page | 5 | 2 | 3
29 | Remember me | 2 | 5
35 | Add remove item in inventory | 4 | 4 | 3
37 | Implement inventory search feature | 3 | 2 | 3
38 | Investigate the server that will hold the app | 5 | 5 | 3
39 | Communicate with Server IT to get access | 5 | 5 | 3
42 | Add Modal to input orders on order details page | 2 | 3 | 3
45 | Implement edit button for jobs page | 2 | 3 | 3
46 | Implement delete button for jobs | 2 | 3 | 3
47 | Create a table for estimates and figure out calculation | 2 | 3 | 3
50 | Remove the invoice section on the jobs page | 1 | 3 | 3
58 | Fix editing the partnumber of a product | 2 | 4 | 3
61 | Learn how to put an app on a server | 4 | 5 | 3
64 | Implement edit button for purchases page | 2 | 4 | 3
65 | Implement delete button for purchases | 3 | 4 | 3
67 | Implement a lockout feature | 2 | 4 | 3
68 | Add functionality to edit necessary parts | 2 | 4 | 3
69 | Add functionality to edit used parts | 2 | 4 | 3
70 | Add a modal to be able to add parts to necessary | 3 | 5 | 3
71 | Add functionality to remove a necessary part | 2 | 4 | 3
72 | Add functionality to the remove used parts button | 2 | 4 | 3
73 | Add functionality to the move to necessary button | 3 | 4 | 3
74 | Create totals of the prices for Used and necessary parts | 1.5 | 4 | 3
75 | Edit the UI so the Estimate, necessary parts, and used parts sections are stacked | 1 | 4 | 3
76 | Edit the Estimate UI | 0.5 | 4 | 3
77 | Create a scraper for the Estimates page | 5 | 2 | 3
78 | Add a modal to be able to add parts to used + functional | 2 | 4 | 3
79 | Calculate the total prices of the parts in necessary + used | 1 | 3 | 3
80 | Jobs page filter should be filtering through database instead of UI | 2 | 1 | 3
81 | Limit the upload size of a PDF in the estimates page. | 1 | 2 | 3
82 | DNS setup for the server | 1 | 3 | 3
83 | Hosting project on a server | 4 | 5 | 3
84 | Set up a production version of the Docker Compose file for the server | 3 | 4 | 3
85 | Create a modal for jobs Remove function | 2 | 2 | 3
86 | Create a modal for jobs move to used function | 2 | 5 | 3
87 | Create a modal for jobs move to necessary function | 2 | 5 | 3
88 | Create a modal for jobs remove from used | 2 | 4 | 3
89 | Create a modal for jobs remove from necessary | 2 | 4 | 3
90 | Add estimate file name in estimate box | 1 | 5 | 3
91 | Implement logging page for all features in the application | 3 | 4 | 3
92 | log actions when adding product in inventory | 1 | 3 | 3
93 | log actions when removing product in inventory | 1 | 2 | 3
94 | log actions fro editing product details in inventory | 1 | 2 | 3
95 | log actions for editing product instock quantity in inventory | 1 | 3 | 3
96 | Fix topbar implementation on mobile | 4 | 5 | 3
97 | Fix the mobile look for inventory | 1 | 3 | 3
98 | Remove checkboxes and filter headers from mobile look | 1 | 3 | 3
99 | Adjust inventory table sizing and display on mobile | 3 | 3 | 3
100 | Fix logging for inventory | 2 | 5 | 3
101 | Implement logging for adding jobs | 6 | 3 | 3
102 | Setup GitHub action to automatically run Cypress Test whenever a pull request is made to the main branch | 2 | 4 | 3
103 | Setup GitHub action to automatically update server whenever merge is made to the main branch | 1 | 5 | 3
104 | Log actions when adding a job | 1 | 5 | 3
105 | Log actions when adding an estimate to a job | 1 | 5 | 3
106 | Log actions when adding a necessary part | 1 | 5 | 3
107 | Log actions when adding a used part | 1 | 5 | 3
108 | Log actions when moving to used | 1 | 5 | 3
109 | Log actions when moving to necessary | 1 | 5 | 3
110 | Log actions when removing part | 1 | 5 | 3
111 | Log actions when editing quantity needed | 1 | 5 | 3
112 | Jobs - Create modals for all functions | 7 | 5 | 3
113 | Make the dashboard based on live data in database | 3 | 1 | 3
114 | Change graphical data to tabled data for product stock dashboard | 3 | 2 | 3
115 | Create initial setup modal for first user | 4 | 4 | 3
116 | Move initial setup modal to login | 2 | 4 | 3
117 | Remove autoregister first user | 2 | 4 | 3
118 | Remove Register route in App.js | 1 | 2 | 3
119 | Implement Role Based Access Control | 6 | 5 | 3
120 | Move register new user to dropdown in topbar | 3 | 3 | 3
121 | Implement manage users to change permissions of users or remove them | 4 | 5 | 3
122 | Implement check to always have 1 admin in the app | 2 | 4 | 3
123 | Hide logs from people who are not role admin | 3 | 5 | 3
124 | Add modals to Purchases Page | 2 | 2 | 3
125 | Create pdf scraper for Purchase orders | 6 | 1
126 | Email verification | 2 | 1
127 | Access in house Guaranty metal server (waiting on server installation) | 8 | 1
128 | Put app on in house guaranty metal server (waiting on server installation) | 6 | 1
129 | Update json web token for editing profile username | 2 | 4 | 3
130 | Update json web token for editing profile password | 2 | 4 | 3
131 | Update json web token for editing profile role | 2 | 4 | 3
132 | Update Database to reflect new purchases page tables | 2 | 5 | 3
133 | Rebuild data structure to work with new tables on purchases | 2 | 5 | 3
134 | Implement api's for moving items into a new order from low and out of stock | 7 | 5 | 3
135 | Implement front end purchases page | 8 | 5 | 3
136 | Implement status logic for purchases | 3 | 5 | 3
137 | Implement inventory updates based off of status logic | 3 | 5 | 3
138 | Implement mark up price to use shipping costs | 3 | 4 | 3
139 | Create the generate xlsx button for purchases | 4 | 4 | 3
140 | Implement delete orders function with confirmation | 3 | 3 | 3
141 | Update modals for purchases | 2 | 3 | 3
142 | Add Testing for the Jobs page on Cypress | 4 | 5 | 3
143 | Edit the upload estimate button so you cannot upload if there is no file chosen | 1 | 4 | 3
144 | Add logging for purchases | 4 | 4 | 3
145 | Upload invoice pdf implementation | 2 | 2
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229